## RABillBrowse_Contwise6386158673
Contractor RA Bill
NEPTUNE OBELISK EXP
Page 1 of 1
Total Records: 61 Records 1 To 61
Contractor | WO NO | RA Bill | RA Bill Date | Project | Labour_Name | TASK | Revision | Qty | Unit | Rate | Payment Schedule | PS % | Retaintion | Retention_amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Net Amount | Status
K K CONSTRUCTION | 21 | 47 | 2021-10-14 | NEPTUNE OBELISK EXP | DEPART SHUTTERING CARPENTER | GROUND FLOOR RCC WORK FOR SLAB | 0 | 25 | NOS | 500 | 100% Completion | 100 | 625 | 625 | 12500 | C + SGST 18% I/P RD | 2250 | 14750 | 14125 | Approved
K K CONSTRUCTION | 21 | 26 | 2021-03-17 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | UPPER BASEMENT PLASTER WORK | 0 | 7094.51 | SQFT | 82 | 100% Completion | 100 | 29087.491 | 84352 | 581749.82 | C + SGST 18% I/P RD | 303669.82 | 885419.64 | 856332.149 | Approved
K K CONSTRUCTION | 21 | 49 | 2021-10-25 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | UPPER BASEMENT PLASTER WORK | 0 | 1138.71 | SQFT | 82 | 100% Completion | 100 | 4668.711 | 40151.21 | 93374.22 | C + SGST 18% I/P RD | 144544.36 | 237918.58 | 233249.869 | Approved
K K CONSTRUCTION | 21 | 90 | 2022-04-25 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | UPPER BASEMENT PLASTER WORK | 0 | 6952.62 | SQFT | 82 | 100% Completion | 100 | 28505.742 | 57011.48 | 570114.84 | C + SGST 18% I/P RD | 95744.28 | 665859.12 | 637353.378 | Approved
K K CONSTRUCTION | 21 | 144 | 2022-09-17 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | UPPER BASEMENT PLASTER WORK | 0 | 6243.17 | SQFT | 82 | 100% Completion | 100 | 25596.997 | 25597 | 511939.94 | C + SGST 18% I/P RD | 92149.18 | 604089.12 | 578492.123 | Approved
K K CONSTRUCTION | 21 | 172 | 2022-11-25 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | GROUND FLOOR PLASTER WORK | 0 | 9268.14 | SQFT | 61.5 | 100% Completion | 100 | 28499.5305 | 67350.48 | 569990.61 | C + SGST 18% I/P RD | 242461.7 | 812452.31 | 783952.7795 | Approved
K K CONSTRUCTION | 21 | 313 | 2023-11-11 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 10TH FLOOR PLASTER WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 37559.48 | 375594.85 | C + SGST 18% I/P RD | 135214.16 | 510809.01 | 492029.2675 | Approved
K K CONSTRUCTION | 21 | 90 | 2022-04-25 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | LOWER BASEMENT PLASTER WORK PLASTER WORK | 0 | 6952.62 | SQFT | 82 | 100% Completion | 100 | 28505.742 | 57011.48 | 570114.84 | C + SGST 18% I/P RD | 95744.28 | 665859.12 | 637353.378 | Approved
K K CONSTRUCTION | 21 | 238 | 2023-05-05 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 6TH FLOOR PLASTER WORK | 0 | 9294.83 | SQFT | 41 | 100% Completion | 100 | 19054.4015 | 19851.26 | 381088.03 | C + SGST 18% I/P RD | 71464.52 | 452552.55 | 433498.1485 | Approved
K K CONSTRUCTION | 21 | 238 | 2023-05-05 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 6TH FLOOR PLASTER WORK | 0 | 388.71 | SQFT | 41 | 100% Completion | 100 | 796.8555 | 19851.26 | 15937.11 | C + SGST 18% I/P RD | 71464.52 | 87401.63 | 86604.7745 | Approved
K K CONSTRUCTION | 21 | 305 | 2023-10-25 18:36 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 7TH FLOOR PLASTER WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 37559.48 | 375594.85 | C + SGST 18% I/P RD | 135214.16 | 510809.01 | 492029.2675 | Approved
K K CONSTRUCTION | 21 | 219 | 2023-02-20 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 4TH FLOOR PLASTER WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 37559.48 | 375594.85 | C + SGST 18% I/P RD | 135214.16 | 510809.01 | 492029.2675 | Approved
K K CONSTRUCTION | 21 | 305 | 2023-10-25 18:36 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 8TH FLOOR PLASTER WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 37559.48 | 375594.85 | C + SGST 18% I/P RD | 135214.16 | 510809.01 | 492029.2675 | Approved
K K CONSTRUCTION | 21 | 26 | 2021-03-17 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | LOWER BASEMENT PLASTER WORK PLASTER WORK | 0 | 5955.79 | SQFT | 82 | 100% Completion | 100 | 24418.739 | 84352 | 488374.78 | C + SGST 18% I/P RD | 303669.82 | 792044.6 | 767625.861 | Approved
K K CONSTRUCTION | 21 | 172 | 2022-11-25 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 1ST FLOOR PLASTER WORK | 0 | 9268.14 | SQFT | 41 | 100% Completion | 100 | 18999.687 | 67350.48 | 379993.74 | C + SGST 18% I/P RD | 242461.7 | 622455.44 | 603455.753 | Approved
K K CONSTRUCTION | 21 | 172 | 2022-11-25 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 2ND FLOOR PLASTER WORK | 0 | 9294.83 | SQFT | 41 | 100% Completion | 100 | 19054.4015 | 67350.48 | 381088.03 | C + SGST 18% I/P RD | 242461.7 | 623549.73 | 604495.3285 | Approved
K K CONSTRUCTION | 21 | 172 | 2022-11-25 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 2ND FLOOR PLASTER WORK | 0 | 388.71 | SQFT | 41 | 100% Completion | 100 | 796.8555 | 67350.48 | 15937.11 | C + SGST 18% I/P RD | 242461.7 | 258398.81 | 257601.9545 | Approved
K K CONSTRUCTION | 21 | 219 | 2023-02-20 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 5TH FLOOR PLASTER WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 37559.48 | 375594.85 | C + SGST 18% I/P RD | 135214.16 | 510809.01 | 492029.2675 | Approved
K K CONSTRUCTION | 21 | 313 | 2023-11-11 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 11TH FLOOR PLASTER WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 37559.48 | 375594.85 | C + SGST 18% I/P RD | 135214.16 | 510809.01 | 492029.2675 | Approved
K K CONSTRUCTION | 21 | 182 | 2022-12-14 | NEPTUNE OBELISK EXP | LABOR FOR INTERNAL PLASTER (SQFT) | 3RD FLOOR PLASTER WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 18779.74 | 375594.85 | C + SGST 18% I/P RD | 67607.08 | 443201.93 | 424422.1875 | Approved
K K CONSTRUCTION | 21 | 368 | 2024-03-20 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 12TH FLOOR MASONRY WORK | 0 | 9294.83 | SQFT | 41 | 100% Completion | 100 | 19054.4015 | 38631 | 381088.03 | C + SGST 18% I/P RD | 139071.6 | 520159.63 | 501105.2285 | Approved
K K CONSTRUCTION | 21 | 368 | 2024-03-20 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 12TH FLOOR MASONRY WORK | 0 | 388.71 | SQFT | 41 | 100% Completion | 100 | 796.8555 | 38631 | 15937.11 | C + SGST 18% I/P RD | 139071.6 | 155008.71 | 154211.8545 | Approved
K K CONSTRUCTION | 21 | 220 | 2023-02-20 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 6TH FLOOR MASONRY WORK | 0 | 9294.83 | SQFT | 41 | 100% Completion | 100 | 19054.4015 | 38631 | 381088.03 | C + SGST 18% I/P RD | 139071.6 | 520159.63 | 501105.2285 | Approved
K K CONSTRUCTION | 21 | 220 | 2023-02-20 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 6TH FLOOR MASONRY WORK | 0 | 388.71 | SQFT | 41 | 100% Completion | 100 | 796.8555 | 38631 | 15937.11 | C + SGST 18% I/P RD | 139071.6 | 155008.71 | 154211.8545 | Approved
K K CONSTRUCTION | 21 | 277 | 2023-08-29 15:09 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 10TH FLOOR MASONRY WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 18779.74 | 375594.85 | C + SGST 18% I/P RD | 67607.08 | 443201.93 | 424422.1875 | Approved
K K CONSTRUCTION | 21 | 368 | 2024-03-20 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 13TH FLOOR MASONRY WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 38631 | 375594.85 | C + SGST 18% I/P RD | 139071.6 | 514666.45 | 495886.7075 | Approved
K K CONSTRUCTION | 21 | 151 | 2022-09-22 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 2ND FLOOR MASONRY WORK | 0 | 9294.83 | SQFT | 41 | 100% Completion | 100 | 19054.4015 | 38850.95 | 381088.03 | C + SGST 18% I/P RD | 139863.4 | 520951.43 | 501897.0285 | Approved
K K CONSTRUCTION | 21 | 151 | 2022-09-22 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 2ND FLOOR MASONRY WORK | 0 | 388.71 | SQFT | 41 | 100% Completion | 100 | 796.8555 | 38850.95 | 15937.11 | C + SGST 18% I/P RD | 139863.4 | 155800.51 | 155003.6545 | Approved
K K CONSTRUCTION | 21 | 220 | 2023-02-20 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 5TH FLOOR MASONRY WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 38631 | 375594.85 | C + SGST 18% I/P RD | 139071.6 | 514666.45 | 495886.7075 | Approved
K K CONSTRUCTION | 21 | 261 | 2023-07-27 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 8TH FLOOR MASONRY WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 18779.74 | 375594.85 | C + SGST 18% I/P RD | 67607.08 | 443201.93 | 424422.1875 | Approved
K K CONSTRUCTION | 21 | 171 | 2022-11-25 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 3RD FLOOR MASONRY WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 37559.48 | 375594.85 | C + SGST 18% I/P RD | 135214.16 | 510809.01 | 492029.2675 | Approved
K K CONSTRUCTION | 21 | 237 | 2023-05-05 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 7TH FLOOR MASONRY WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 18779.74 | 375594.85 | C + SGST 18% I/P RD | 67607.08 | 443201.93 | 424422.1875 | Approved
K K CONSTRUCTION | 21 | 106 | 2022-06-09 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | GROUND FLOOR MASONRY WORK | 0 | 9268.14 | SQFT | 61.5 | 100% Completion | 100 | 28499.5305 | 28499.53 | 569990.61 | C + SGST 18% I/P RD | 102598.3 | 672588.91 | 644089.3795 | Approved
K K CONSTRUCTION | 21 | 312 | 2023-11-11 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 11TH FLOOR MASONRY WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 18779.74 | 375594.85 | C + SGST 18% I/P RD | 67607.08 | 443201.93 | 424422.1875 | Approved
K K CONSTRUCTION | 21 | 151 | 2022-09-22 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 1ST FLOOR MASONRY WORK | 0 | 9268.14 | SQFT | 41 | 100% Completion | 100 | 18999.687 | 38850.95 | 379993.74 | C + SGST 18% I/P RD | 139863.4 | 519857.14 | 500857.453 | Approved
K K CONSTRUCTION | 21 | 171 | 2022-11-25 | NEPTUNE OBELISK EXP | LABOUR FOR BLOCK WORK (SQFT) | 4TH FLOOR MASONRY WORK | 0 | 9160.85 | SQFT | 41 | 100% Completion | 100 | 18779.7425 | 37559.48 | 375594.85 | C + SGST 18% I/P RD | 135214.16 | 510809.01 | 492029.2675 | Approved
K K CONSTRUCTION | 21 | 235 | 2023-05-15 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 10TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 155 | 100% Completion | 100 | 70996.5875 | 70996.59 | 1419931.75 | C + SGST 18% I/P RD | 255587.72 | 1675519.47 | 1604522.8825 | Approved
K K CONSTRUCTION | 21 | 288 | 2023-09-29 19:22 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 13TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 191 | 100% Completion | 100 | 87486.1175 | 87486.12 | 1749722.35 | C + SGST 18% I/P RD | 314950.02 | 2064672.37 | 1977186.2525 | Approved
K K CONSTRUCTION | 21 | 81 | 2022-03-15 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 2ND FLOOR RCC WORK FOR SLAB | 0 | 9294.83 | SQFT | 155 | 100% Completion | 100 | 72034.9325 | 75020 | 1440698.65 | C + SGST 18% I/P RD | 270072 | 1710770.65 | 1638735.7175 | Approved
K K CONSTRUCTION | 21 | 81 | 2022-03-15 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 2ND FLOOR RCC WORK FOR SLAB | 0 | 385.17 | SQFT | 155 | 100% Completion | 100 | 2985.0675 | 75020 | 59701.35 | C + SGST 18% I/P RD | 270072 | 329773.35 | 326788.2825 | Approved
K K CONSTRUCTION | 21 | 120 | 2022-07-21 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 4TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 155 | 100% Completion | 100 | 70996.5875 | 70996.59 | 1419931.75 | C + SGST 18% I/P RD | 255587.72 | 1675519.47 | 1604522.8825 | Approved
K K CONSTRUCTION | 21 | 178 | 2022-12-10 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 7TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 155 | 100% Completion | 100 | 70996.5875 | 70996.59 | 1419931.75 | C + SGST 18% I/P RD | 255587.72 | 1675519.47 | 1604522.8825 | Approved
K K CONSTRUCTION | 21 | 26 | 2021-03-17 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | LOWER BASEMENT RCC WORK | 0 | 1047 | SQFT | 190 | 100% Completion | 100 | 9946.5 | 84352 | 198930 | C + SGST 18% I/P RD | 303669.82 | 502599.82 | 492653.32 | Approved
K K CONSTRUCTION | 21 | 107 | 2022-06-13 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 3RD FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 155 | 100% Completion | 100 | 70996.5875 | 70996.59 | 1419931.75 | C + SGST 18% I/P RD | 255587.72 | 1675519.47 | 1604522.8825 | Approved
K K CONSTRUCTION | 21 | 26 | 2021-03-17 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | UPPER BASEMENT RCC WORK - SQFT | 0 | 2200 | SQFT | 190 | 100% Completion | 100 | 20900 | 84352 | 418000 | C + SGST 18% I/P RD | 303669.82 | 721669.82 | 700769.82 | Approved
K K CONSTRUCTION | 21 | 49 | 2021-10-25 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | UPPER BASEMENT RCC WORK - SQFT | 0 | 3735 | SQFT | 190 | 100% Completion | 100 | 35482.5 | 40151.21 | 709650 | C + SGST 18% I/P RD | 144544.36 | 854194.36 | 818711.86 | Approved
K K CONSTRUCTION | 21 | 333 | 2024-01-20 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 16TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 191 | 100% Completion | 100 | 87486.1175 | 87486.12 | 1749722.35 | C + SGST 18% I/P RD | 314950.02 | 2064672.37 | 1977186.2525 | Approved
K K CONSTRUCTION | 21 | 145 | 2022-09-17 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 5TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 155 | 100% Completion | 100 | 70996.5875 | 70996.59 | 1419931.75 | C + SGST 18% I/P RD | 255587.72 | 1675519.47 | 1604522.8825 | Approved
K K CONSTRUCTION | 21 | 207 | 2023-02-01 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 8TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 155 | 100% Completion | 100 | 70996.5875 | 70996.59 | 1419931.75 | C + SGST 18% I/P RD | 255587.72 | 1675519.47 | 1604522.8825 | Approved
K K CONSTRUCTION | 21 | 162 | 2022-11-07 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 6TH FLOOR RCC WORK FOR SLAB | 0 | 388.71 | SQFT | 155 | 100% Completion | 100 | 3012.5025 | 75047.43 | 60250.05 | C + SGST 18% I/P RD | 270170.76 | 330420.81 | 327408.3075 | Approved
K K CONSTRUCTION | 21 | 226 | 2023-03-20 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 9TH FLOOR RCC WORK FOR SLAB | 0 | 9294.83 | SQFT | 155 | 100% Completion | 100 | 72034.9325 | 75047.43 | 1440698.65 | C + SGST 18% I/P RD | 270170.76 | 1710869.41 | 1638834.4775 | Approved
K K CONSTRUCTION | 21 | 226 | 2023-03-20 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 9TH FLOOR RCC WORK FOR SLAB | 0 | 388.71 | SQFT | 155 | 100% Completion | 100 | 3012.5025 | 75047.43 | 60250.05 | C + SGST 18% I/P RD | 270170.76 | 330420.81 | 327408.3075 | Approved
K K CONSTRUCTION | 21 | 260 | 2023-07-27 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 11TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 191 | 100% Completion | 100 | 87486.1175 | 87486.12 | 1749722.35 | C + SGST 18% I/P RD | 314950.02 | 2064672.37 | 1977186.2525 | Approved
K K CONSTRUCTION | 21 | 304 | 2023-10-25 18:26 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 14TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 191 | 100% Completion | 100 | 87486.1175 | 87486.12 | 1749722.35 | C + SGST 18% I/P RD | 314950.02 | 2064672.37 | 1977186.2525 | Approved
K K CONSTRUCTION | 21 | 359 | 2024-03-07 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 17TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 191 | 100% Completion | 100 | 87486.1175 | 87486.12 | 1749722.35 | C + SGST 18% I/P RD | 314950.02 | 2064672.37 | 1977186.2525 | Approved
K K CONSTRUCTION | 21 | 42 | 2021-09-15 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | GROUND FLOOR RCC WORK FOR SLAB | 0 | 9294.83 | SQFT | 247.5 | 100% Completion | 100 | 115023.5213 | 115024 | 2300470.43 | C + SGST 18% I/P RD | 414084.68 | 2714555.105 | 2599531.5838 | Approved
K K CONSTRUCTION | 21 | 276 | 2023-08-29 14:59 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 12TH FLOOR RCC WORK FOR SLAB | 0 | 9683.54 | SQFT | 191 | 100% Completion | 100 | 92477.807 | 92477.81 | 1849556.14 | C + SGST 18% I/P RD | 332920.1 | 2182476.24 | 2089998.433 | Approved
K K CONSTRUCTION | 21 | 321 | 2023-12-20 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 15TH FLOOR RCC WORK FOR SLAB | 0 | 9683.54 | SQFT | 191 | 100% Completion | 100 | 92477.807 | 92477.81 | 1849556.14 | C + SGST 18% I/P RD | 332920.1 | 2182476.24 | 2089998.433 | Approved
K K CONSTRUCTION | 21 | 369 | 2024-03-20 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 18TH FLOOR RCC WORK FOR SLAB | 0 | 9160.85 | SQFT | 191 | 100% Completion | 100 | 87486.1175 | 87486.12 | 1749722.35 | C + SGST 18% I/P RD | 314950.02 | 2064672.37 | 1977186.2525 | Approved
K K CONSTRUCTION | 21 | 60 | 2021-12-24 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 1ST FLOOR RCC WORK FOR SLAB | 0 | 9268.14 | SQFT | 155 | 100% Completion | 100 | 71828.085 | 71828.09 | 1436561.7 | C + SGST 18% I/P RD | 139987.56 | 1576549.26 | 1504721.175 | Approved
K K CONSTRUCTION | 21 | 162 | 2022-11-07 | NEPTUNE OBELISK EXP | LABOUR FOR RCC | 6TH FLOOR RCC WORK FOR SLAB | 0 | 9294.83 | SQFT | 155 | 100% Completion | 100 | 72034.9325 | 75047.43 | 1440698.65 | C + SGST 18% I/P RD | 270170.76 | 1710869.41 | 1638834.4775 | Approved