## RABillBrowse_Contwise6386182705
Contractor RA Bill
GREENWOODS ABODE
Page 1 of 1
Total Records: 34 Records 1 To 34
Contractor | WO NO | RA Bill | RA Bill Date | Project | Labour_Name | TASK | Revision | Qty | Unit | Rate | Payment Schedule | PS % | Retaintion | Retention_amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Net Amount | Status
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 48 | 2022-10-13 | GREENWOODS ABODE | LABBOR FOR CONCRETE M30 (CMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 457.71 | CMT | 4967.4 | 100% Completion | 100 | 113681.4327 | 429111.8 | 2273628.65 | C + SGST 18% I/P RD | 1544802.52 | 3818431.174 | 3704749.7413 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 117 | 2024-05-01 | GREENWOODS ABODE | LABBOR FOR CONCRETE M30 (CMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 384.54 | CMT | 4967.4 | 100% Completion | 100 | 95508.1998 | 165254.24 | 1910164 | C + SGST 18% I/P RD | 594915.32 | 2505079.316 | 2409571.1162 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 117 | 2024-05-01 | GREENWOODS ABODE | LABBOR FOR CONCRETE M30 (CMT) | TOWER B GROUND FLOOR CIVIL WORK | 0 | 125.85 | CMT | 4967.4 | 100% Completion | 100 | 31257.3645 | 165254.24 | 625147.29 | C + SGST 18% I/P RD | 594915.32 | 1220062.61 | 1188805.2455 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 34 | 2022-07-29 | GREENWOODS ABODE | LABOR FOR CENTERING & FORM WORK (SQMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 173.66 | SQMT | 511.35 | 100% Completion | 100 | 4440.0521 | 161754.2 | 88801.04 | C + SGST 18% I/P RD | 582315.14 | 671116.181 | 666676.129 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 48 | 2022-10-13 | GREENWOODS ABODE | LABOR FOR CENTERING & FORM WORK (SQMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 249.38 | SQMT | 511.35 | 100% Completion | 100 | 6376.0231 | 429111.8 | 127520.46 | C + SGST 18% I/P RD | 1544802.52 | 1672322.983 | 1665946.9599 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 101 | 2023-11-09 | GREENWOODS ABODE | LABOR FOR CENTERING & FORM WORK (SQMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 2037.61 | SQMT | 511.35 | 100% Completion | 100 | 52096.5886 | 251442.18 | 1041931.77 | C + SGST 18% I/P RD | 905191.8 | 1947123.5712 | 1895026.9827 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 48 | 2022-10-13 | GREENWOODS ABODE | LABOR FOR CENTERING & FORM WORK (SQMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 179.33 | SQMT | 511.35 | 100% Completion | 100 | 4585.0198 | 429111.8 | 91700.4 | C + SGST 18% I/P RD | 1544802.52 | 1636502.9155 | 1631917.8957 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 101 | 2023-11-09 | GREENWOODS ABODE | LABOR FOR CENTERING & FORM WORK (SQMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 6.88 | SQMT | 511.35 | 100% Completion | 100 | 175.7766 | 251442.18 | 3515.53 | C + SGST 18% I/P RD | 905191.8 | 908707.3313 | 908531.5547 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 117 | 2024-05-01 | GREENWOODS ABODE | LABOR FOR CENTERING & FORM WORK (SQMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 522.93 | SQMT | 511.35 | 100% Completion | 100 | 13370.0332 | 165254.24 | 267400.66 | C + SGST 18% I/P RD | 594915.32 | 862315.9846 | 848945.9514 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 33 | 2022-07-29 | GREENWOODS ABODE | LABOR FOR RMC SUPPLY FROM OUTSIDE (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 224.6 | CMT | 400 | 100% Completion | 100 | 4492 | 47150.28 | 89840 | C + SGST 18% I/P RD | 169741 | 259581 | 255089 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 34 | 2022-07-29 | GREENWOODS ABODE | LABOR FOR RMC SUPPLY FROM OUTSIDE (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 172.47 | CMT | 400 | 100% Completion | 100 | 3449.4 | 161754.2 | 68988 | C + SGST 18% I/P RD | 582315.14 | 651303.14 | 647853.74 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 101 | 2023-11-09 | GREENWOODS ABODE | LABOR FOR RMC SUPPLY FROM OUTSIDE (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 574.01 | CMT | 400 | 100% Completion | 100 | 11480.2 | 251442.18 | 229604 | C + SGST 18% I/P RD | 905191.8 | 1134795.8 | 1123315.6 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 34 | 2022-07-29 | GREENWOODS ABODE | LABOR FOR RMC SUPPLY FROM OUTSIDE (CMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 213.4 | CMT | 400 | 100% Completion | 100 | 4268 | 161754.2 | 85360 | C + SGST 18% I/P RD | 582315.14 | 667675.14 | 663407.14 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 101 | 2023-11-09 | GREENWOODS ABODE | LABOR FOR RMC SUPPLY FROM OUTSIDE (CMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 43.94 | CMT | 400 | 100% Completion | 100 | 878.718 | 251442.18 | 17574.36 | C + SGST 18% I/P RD | 905191.8 | 922766.16 | 921887.442 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 33 | 2022-07-29 | GREENWOODS ABODE | LABOUR FOR PCC (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 224.6 | CMT | 3798.6 | 100% Completion | 100 | 42658.278 | 47150.28 | 853165.56 | C + SGST 18% I/P RD | 169741 | 1022906.56 | 980248.282 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 34 | 2022-07-29 | GREENWOODS ABODE | LABOUR FOR PCC (CMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 212.95 | CMT | 3798.6 | 100% Completion | 100 | 40445.5935 | 161754.2 | 808911.87 | C + SGST 18% I/P RD | 582315.14 | 1391227.01 | 1350781.4165 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 101 | 2023-11-09 | GREENWOODS ABODE | LABOUR FOR PCC (CMT) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 43.94 | CMT | 3798.6 | 100% Completion | 100 | 8344.7455 | 251442.18 | 166894.91 | C + SGST 18% I/P RD | 905191.8 | 1072086.7097 | 1063741.9643 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 34 | 2022-07-29 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 17.8 | TONN | 74511 | 100% Completion | 100 | 66314.79 | 161754.2 | 1326295.8 | C + SGST 18% I/P RD | 582315.14 | 1908610.94 | 1842296.15 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 48 | 2022-10-13 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 17.8 | TONN | 74511 | 100% Completion | 100 | 66314.79 | 429111.8 | 1326295.8 | C + SGST 18% I/P RD | 1544802.52 | 2871098.32 | 2804783.53 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 101 | 2023-11-09 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 19.94 | TONN | 74511 | 100% Completion | 100 | 74298.6436 | 251442.18 | 1485972.87 | C + SGST 18% I/P RD | 905191.8 | 2391164.673 | 2316866.0294 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 115 | 2024-04-30 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 4.58 | TONN | 74511 | 100% Completion | 100 | 17077.1761 | 128134.71 | 341543.52 | C + SGST 18% I/P RD | 461284.94 | 802828.4618 | 785751.2857 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 116 | 2024-04-30 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 3.16 | TONN | 74511 | 100% Completion | 100 | 11784.6598 | 128817.97 | 235693.2 | C + SGST 18% I/P RD | 463744.7 | 699437.8952 | 687653.2354 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 48 | 2022-10-13 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 52.98 | TONN | 74511 | 100% Completion | 100 | 197379.639 | 429111.8 | 3947592.78 | C + SGST 18% I/P RD | 1544802.52 | 5492395.3 | 5295015.661 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 101 | 2023-11-09 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 27.96 | TONN | 74511 | 100% Completion | 100 | 104167.4957 | 251442.18 | 2083349.91 | C + SGST 18% I/P RD | 905191.8 | 2988541.7133 | 2884374.2176 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 115 | 2024-04-30 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER A UP TO PLINTH CIVIL WORK | 0 | 29.81 | TONN | 74511 | 100% Completion | 100 | 111057.5278 | 128134.71 | 2221150.56 | C + SGST 18% I/P RD | 461284.94 | 2682435.4967 | 2571377.9689 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 116 | 2024-04-30 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B GROUND FLOOR CIVIL WORK | 0 | 0 | TONN | 74511 | 100% Completion | 100 | 0.37256 | 128817.97 | 7.45 | C + SGST 18% I/P RD | 463744.7 | 463752.1511 | 463751.7785 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 116 | 2024-04-30 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B GROUND FLOOR CIVIL WORK | 0 | 31.41 | TONN | 74511 | 100% Completion | 100 | 117032.9375 | 128817.97 | 2340658.75 | C + SGST 18% I/P RD | 463744.7 | 2804403.4496 | 2687370.5121 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 117 | 2024-05-01 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B GROUND FLOOR CIVIL WORK | 0 | 0.79 | TONN | 74511 | 100% Completion | 100 | 2926.7921 | 165254.24 | 58535.84 | C + SGST 18% I/P RD | 594915.32 | 653451.1616 | 650524.3695 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 118 | 2024-05-01 | GREENWOODS ABODE | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | TOWER B GROUND FLOOR CIVIL WORK | 0 | 12.51 | TONN | 74511 | 100% Completion | 100 | 46609.9835 | 46609.98 | 932199.67 | C + SGST 18% I/P RD | 167795.94 | 1099995.6099 | 1053385.6264 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 79 | 2023-05-08 | GREENWOODS ABODE | LABBOR FOR CONCRETE M30 (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 391.94 | CMT | 4967.4 | 100% Completion | 100 | 97346.1378 | 142566.87 | 1946922.76 | C + SGST 18% I/P RD | 513240.72 | 2460163.476 | 2362817.3382 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 48 | 2022-10-13 | GREENWOODS ABODE | LABBOR FOR CONCRETE M30 (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 164.17 | CMT | 4967.4 | 100% Completion | 100 | 40774.9029 | 429111.8 | 815498.06 | C + SGST 18% I/P RD | 1544802.52 | 2360300.578 | 2319525.6751 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 79 | 2023-05-08 | GREENWOODS ABODE | LABBOR FOR CONCRETE M30 (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 182.07 | CMT | 4967.4 | 100% Completion | 100 | 45220.7259 | 142566.87 | 904414.52 | C + SGST 18% I/P RD | 513240.72 | 1417655.238 | 1372434.5121 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 117 | 2024-05-01 | GREENWOODS ABODE | LABBOR FOR CONCRETE M30 (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 89.35 | CMT | 4967.4 | 100% Completion | 100 | 22191.8595 | 165254.24 | 443837.19 | C + SGST 18% I/P RD | 594915.32 | 1038752.51 | 1016560.6505 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 34 | 2022-07-29 | GREENWOODS ABODE | LABBOR FOR CONCRETE M30 (CMT) | TOWER B UP TO PLINTH CIVIL WORK | 0 | 172.47 | CMT | 4967.4 | 100% Completion | 100 | 42836.3739 | 161754.2 | 856727.48 | C + SGST 18% I/P RD | 582315.14 | 1439042.618 | 1396206.2441 | Approved