## RABillBrowse_Contwise6386848786
Contractor RA Bill
GREENWOODS AARANYA
Page 1 of 1
Total Records: 36 Records 1 To 36
Contractor | WO NO | RA Bill | RA Bill Date | Project | Labour_Name | TASK | Revision | Qty | Unit | Rate | Payment Schedule | PS % | Retaintion | Retention_amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Net Amount | Status
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 1ST FLOOR RCC WORK FOR SLAB | 0 | 5888.43 | SQFT | 55.5 | 100% Completion | 100 | 16340.3932 | 367343.32 | 326807.87 | C + SGST 18% I/P RD | 1322435.82 | 1649243.685 | 1632903.2918 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 2ND FLOOR RCC WORK FOR SLAB | 0 | 5709.02 | SQFT | 55.5 | 100% Completion | 100 | 15842.5305 | 367343.32 | 316850.61 | C + SGST 18% I/P RD | 1322435.82 | 1639286.43 | 1623443.8995 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 3RD FLOOR RCC WORK FOR SLAB | 0 | 5709.02 | SQFT | 55.5 | 100% Completion | 100 | 15842.5305 | 367343.32 | 316850.61 | C + SGST 18% I/P RD | 1322435.82 | 1639286.43 | 1623443.8995 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 4TH FLOOR RCC WORK FOR SLAB | 0 | 5709.02 | SQFT | 55.5 | 100% Completion | 100 | 15842.5305 | 367343.32 | 316850.61 | C + SGST 18% I/P RD | 1322435.82 | 1639286.43 | 1623443.8995 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 5TH FLOOR RCC WORK FOR SLAB | 0 | 5709.02 | SQFT | 55.5 | 100% Completion | 100 | 15842.5305 | 367343.32 | 316850.61 | C + SGST 18% I/P RD | 1322435.82 | 1639286.43 | 1623443.8995 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 6TH FLOOR RCC WORK FOR SLAB | 0 | 5709.02 | SQFT | 55.5 | 100% Completion | 100 | 15842.5305 | 367343.32 | 316850.61 | C + SGST 18% I/P RD | 1322435.82 | 1639286.43 | 1623443.8995 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 7TH FLOOR RCC WORK FOR SLAB | 0 | 5709.02 | SQFT | 55.5 | 100% Completion | 100 | 15842.5305 | 367343.32 | 316850.61 | C + SGST 18% I/P RD | 1322435.82 | 1639286.43 | 1623443.8995 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 8TH FLOOR RCC WORK FOR SLAB | 0 | 5709.02 | SQFT | 55.5 | 100% Completion | 100 | 15842.5305 | 367343.32 | 316850.61 | C + SGST 18% I/P RD | 1322435.82 | 1639286.43 | 1623443.8995 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 9TH FLOOR RCC WORK FOR SLAB | 0 | 5709.02 | SQFT | 55.5 | 100% Completion | 100 | 15842.5305 | 367343.32 | 316850.61 | C + SGST 18% I/P RD | 1322435.82 | 1639286.43 | 1623443.8995 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 10TH FLOOR RCC WORK FOR SLAB | 0 | 5419.02 | SQFT | 55.5 | 100% Completion | 100 | 15037.7805 | 367343.32 | 300755.61 | C + SGST 18% I/P RD | 1322435.82 | 1623191.43 | 1608153.6495 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 11TH FLOOR RCC WORK FOR SLAB | 0 | 5419.02 | SQFT | 55.5 | 100% Completion | 100 | 15037.7805 | 367343.32 | 300755.61 | C + SGST 18% I/P RD | 1322435.82 | 1623191.43 | 1608153.6495 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 12TH FLOOR RCC WORK FOR SLAB | 0 | 5419.02 | SQFT | 55.5 | 100% Completion | 100 | 15037.7805 | 367343.32 | 300755.61 | C + SGST 18% I/P RD | 1322435.82 | 1623191.43 | 1608153.6495 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D 13TH FLOOR RCC WORK FOR SLAB | 0 | 5419.02 | SQFT | 55.5 | 100% Completion | 100 | 15037.7805 | 367343.32 | 300755.61 | C + SGST 18% I/P RD | 1322435.82 | 1623191.43 | 1608153.6495 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D BASEMENT RCC WORK FOR SLAB | 0 | 15998.7 | SQFT | 67 | 100% Completion | 100 | 53595.645 | 367343.32 | 1071912.9 | C + SGST 18% I/P RD | 1322435.82 | 2394348.72 | 2340753.075 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR RCC SLAB (SQFT) | TOWER D GROUND FLOOR RCC WORK FOR SLAB | 0 | 5757.15 | SQFT | 55.5 | 100% Completion | 100 | 15976.0912 | 367343.32 | 319521.83 | C + SGST 18% I/P RD | 1322435.82 | 1641957.645 | 1625981.5538 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR MASONRY WORK (SQFT) | TOWER D 3RD FLOOR MASONRY WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR MASONRY WORK (SQFT) | TOWER D 4TH FLOOR MASONRY WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR MASONRY WORK (SQFT) | TOWER D 5TH FLOOR MASONRY WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR MASONRY WORK (SQFT) | TOWER D 6TH FLOOR MASONRY WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR MASONRY WORK (SQFT) | TOWER D 7TH FLOOR MASONRY WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR MASONRY WORK (SQFT) | TOWER D 8TH FLOOR MASONRY WORK | 0 | 5419.02 | SQFT | 12.5 | 100% Completion | 100 | 3386.8875 | 367343.32 | 67737.75 | C + SGST 18% I/P RD | 1322435.82 | 1390173.57 | 1386786.6825 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR MASONRY WORK (SQFT) | TOWER D 1ST FLOOR MASONRY WORK | 0 | 5888.43 | SQFT | 12.5 | 100% Completion | 100 | 3680.2688 | 367343.32 | 73605.38 | C + SGST 18% I/P RD | 1322435.82 | 1396041.195 | 1392360.9263 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR MASONRY WORK (SQFT) | TOWER D 2ND FLOOR MASONRY WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR INTERNAL PLASTER (SQFT) | TOWER D GROUND FLOOR PLASTER WORK | 0 | 4317.86 | SQFT | 12.5 | 100% Completion | 100 | 2698.6625 | 367343.32 | 53973.25 | C + SGST 18% I/P RD | 1322435.82 | 1376409.07 | 1373710.4075 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR INTERNAL PLASTER (SQFT) | TOWER D 1ST FLOOR PLASTER WORK | 0 | 5888.43 | SQFT | 12.5 | 100% Completion | 100 | 3680.2688 | 367343.32 | 73605.38 | C + SGST 18% I/P RD | 1322435.82 | 1396041.195 | 1392360.9263 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR INTERNAL PLASTER (SQFT) | TOWER D 2ND FLOOR PLASTER WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR INTERNAL PLASTER (SQFT) | TOWER D 3RD FLOOR PLASTER WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR INTERNAL PLASTER (SQFT) | TOWER D 4TH FLOOR PLASTER WORK | 0 | 5419.02 | SQFT | 12.5 | 100% Completion | 100 | 3386.8875 | 367343.32 | 67737.75 | C + SGST 18% I/P RD | 1322435.82 | 1390173.57 | 1386786.6825 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR INTERNAL PLASTER (SQFT) | TOWER D 5TH FLOOR PLASTER WORK | 0 | 5709.02 | SQFT | 12.5 | 100% Completion | 100 | 3568.1375 | 367343.32 | 71362.75 | C + SGST 18% I/P RD | 1322435.82 | 1393798.57 | 1390230.4325 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR INTERNAL PLASTER (SQFT) | TOWER D 6TH FLOOR PLASTER WORK | 0 | 5419.02 | SQFT | 12.5 | 100% Completion | 100 | 3386.8875 | 367343.32 | 67737.75 | C + SGST 18% I/P RD | 1322435.82 | 1390173.57 | 1386786.6825 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR INTERNAL PLASTER (SQFT) | TOWER D BASEMENT PLASTER WORK | 0 | 15998.43 | SQFT | 28 | 100% Completion | 100 | 22397.802 | 367343.32 | 447956.04 | C + SGST 18% I/P RD | 1322435.82 | 1770391.86 | 1747994.058 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR EXTERNAL PLASTER (SQFT) | TOWER D GROUND FLOOR PLASTER WORK | 0 | 5467.15 | SQFT | 14.5 | 100% Completion | 100 | 3963.6838 | 367343.32 | 79273.68 | C + SGST 18% I/P RD | 1322435.82 | 1401709.495 | 1397745.8113 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR EXTERNAL PLASTER (SQFT) | TOWER D 1ST FLOOR PLASTER WORK | 0 | 5598.43 | SQFT | 14.5 | 100% Completion | 100 | 4058.8618 | 367343.32 | 81177.24 | C + SGST 18% I/P RD | 1322435.82 | 1403613.055 | 1399554.1933 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR EXTERNAL PLASTER (SQFT) | TOWER D 2ND FLOOR PLASTER WORK | 0 | 5419.02 | SQFT | 14.5 | 100% Completion | 100 | 3928.7895 | 367343.32 | 78575.79 | C + SGST 18% I/P RD | 1322435.82 | 1401011.61 | 1397082.8205 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR EXTERNAL PLASTER (SQFT) | TOWER D 3RD FLOOR PLASTER WORK | 0 | 5419.02 | SQFT | 14.5 | 100% Completion | 100 | 3928.7895 | 367343.32 | 78575.79 | C + SGST 18% I/P RD | 1322435.82 | 1401011.61 | 1397082.8205 | Approved
SHREYPATH INFRASTRUCTURE PVT LTD | 10 | 842 | 2024-08-09 | GREENWOODS AARANYA | LABOR FOR EXTERNAL PLASTER (SQFT) | TOWER D 4TH FLOOR PLASTER WORK | 0 | 5419.02 | SQFT | 14.5 | 100% Completion | 100 | 3928.7895 | 367343.32 | 78575.79 | C + SGST 18% I/P RD | 1322435.82 | 1401011.61 | 1397082.8205 | Approved