## RABillBrowse_projwise6386280398
Project RA Bill
GREENWOODS ABODE
Bill Date From 06/07/2007 To 25/09/2024
Page 1 of 1
Total Records: 1 Records 1 To 1
Project | WO NO | RABill Sr.No | RA Bill Date | Cont Bill No | Contractor | Executed_By | Voucher_No | TASK | Labour_Name | Qty | Unit | Rate | PS % | Retention_Amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Total Amount | Status | Credits | Debits | TDS_Amt | Due Date
GREENWOODS ABODE | 24 | 118 | 01 May 2024 | 24-25/10 | SHREYPATH INFRASTRUCTURE PVT LTD | SHREYPATH INFRASTRUCTURE PVT LTD | EV - 92 | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | 12.5109 | TONN | 74511 | 100 | 46609.98 | 932199.67 | C + SGST 18% I/P RD | 167795.94 | 1099995.61 | 1099995.61 | Approved | 0 | 0 | 18644 | 08 May 2024